## Sheet1
Item Name | Status | Scope | Owner | Target Date | Description | Class | Column1
Data Layer
Data Interfaces
IDataDirectory | Done | 0.1 | Mesrop | 2016-07-10 | Provides files content
IDataProvider | Done | 0.1 | Mesrop | 2016-07-10 | Provides ready to be used data to analyzers
IFieldCollection | Done | 0.1 | Mesrop | 2016-07-10 | Interface for getting fields
IFiled Data | Done | 0.1 | Razmik | 2016-11-17 | Represents single filed info (FieldName, Type and the data accessor
IVector, IXVector … | Done | 0.1 | Razmik | 2016-11-17
Data Implementation |  |  |  | 2016-11-17
Data Parser | Ready 60% | 7 | Anna | 2016-11-17 | Parses single file and returns file info
Data Loader | Pending | 4 | Anna | 2016-11-17 | Organizes multiple files parsing
Data Structures |  |  | Razmik | 2016-11-17
File Info | Ready 90% |  | Razmik | 2016-11-17
File Data | In progress 50% |  | Razmik | 2016-11-17
Data Directory | Pending |  |  | 2016-11-17 | Implements IDataDirectory, scans data files and provides field information
Data Provider | Pending |  | Anna | 2016-11-17
Data Selection classes |  |  |  | 2016-11-17
Field (string) | Done | 0.1 | Mesrop | 2016-07-01 | typedef string to Field, it is ID for a Field
Field Value Selection | Ready 90% | 0.1 | Mesrop | 2016-07-15 | Represents single filed with its selection (values, search pattern etc.)
Selection | Ready 90% | 0.3 | Mesrop | 2016-12-01 | It contains all selections of field values
Logic layer |  |  |  | 2016-11-17
Interfaces |  |  |  | 2016-11-17
IAnalyzer | Ready 50% |  | Tamara | 2016-11-17
Configuration | Ready 90% | 1 | Mesrop | 2016-08-10 | Represents information of analyse (Type, Parameter etc.)
ConfigurationLIst | Pending |  |  | 2016-11-17
Configuration Manager | Ready 90% |  | Dro | 2016-11-17
Analysis Selection | Pending |  | Dro | 2016-11-17
Analysis Manager |  |  | Dro | 2016-11-17
Modules |  |  |  | 2016-11-17
Histogram | Pending |  | Liana | 2016-11-17
Wafer Map | Ready 95% | 12 | Mesrop | 2016-12-03 | Wafer analyse: Drow wafer map (support 4 types)
Pareto | Started 0% |  | Tamara | 2016-11-17
Summary tables | Started 0% |  | Seda | 2016-11-17
Application Layer |  |  |  | 2016-11-17
Application | Pending |  | Dro | 2016-11-17
GUI |  |  |  | 2016-11-17
Main Window | Pending |  | Dro | 2016-11-17
Assistant Dialog | Pending |  | Tatevik | 2016-11-17
Data selection Page | Pending |  | Tatevik | 2016-11-17
Analysis selection Page | Pending |  | Tatevik | 2016-11-17
Configuration Editr dialog | Pending |  | Tatevik | 2016-11-17
Histogram Page | In progress 50% |  | Liana | 2016-11-17
Wafer Page | Ready 95% | 0.5 | Mesrop | 2016-09-20 | Wafer Analyse: Paremeter selection page (BinType, Mode)
Pareto Page | In progress 50% |  | Tamara | 2016-11-17
Summary Page | In progress 90% |  | Seda | 2016-11-17
Graphics Layer
Documentation
Architecture | Pending |  | Seda | 2016-11-17
Design specification | Pending |  | Tamara | 2016-11-17
Class hierarchy | Pending |  |  | 2016-11-17
Object hierarchy | Pending |  |  | 2016-11-17